## Critical pre-launch
File:line | What leaks
lambda/api/app.py:3733 | every ValueError, incl. JSON parse errors
lambda/share_viewer/app.py:1268 | catch-all ValueError
lambda/reviewer/app.py:1310 | catch-all ValueError
lambda/signup/app.py:1031-1034 | Cognito's raw Error.Message
lambda/composition/app.py:747 | type(exc).__name__: exc -> Memo.tsx
lambda/composition/app.py:1280 | same, different path
lambda/proposer/app.py:418 | exc.reason strings -> Propose.tsx
lambda/admin/cross_tenant.py:221 | str(exc)[:200], staff-only

## Revert
File:line | Says | Settled truth
ui/src/Account.tsx:891 | "no reversals, ever" | refunds exist since 29 Sept
ui/src/Account.tsx:1143 | Members can "edit and publish" | 17.7: admin-only in code

## Deferrable (summary)
Category | Count | Description
Internal words on screen (R1) | 83 | tenant, bucket, schema, snake_case keys, etc. visible to users
Inconsistent naming (R2) | 36 | one thing called two names: report/memorandum, field/fact, file/engagement
Vague error copy (R3) | 46 | errors with no stated cause or next step
Note: | Full 140-row detail is in the project doc "ARQEDIA Copy Review.html"; not duplicated here. Counts overlap (a finding can break more than one rule).